## KPI Matrix
KPIs Matrix - Time Management |  |  |  | Revision | Code | Date | Status
|  |  |  | Rev01 | KPIs.TM. | 2015-12-21 | Approved
No. | Process Ref. | Owner | Key Result Area | Measurement Method of Results of KRA | Key Performance Indicator | Calculation Method | Weight | Target
KPI-TM-01 | Process.TM.Dev-Sch. Risk Mgmt Process | Planning Engineer | Tender Planning Package | Captured Risk | Accuracy of Risk identification Risk captured at Tendering phase Vs Actual Risk after schedule development | (Count of identified risks at Tendering Phase) - (Count of identified Risks at Developping the schedule phase) To be Developed further Under the Risk Management Process |  | <=0
KPI-TM-02 | Process.TM.Dev-Sch. Intergration Management Process | Quantity Surveyor / Project level | Quantities Breakdown in accordance with the Agreed WBS | Date of issuance of the Quantities Breakdown Report | Timely completion of Quantities BD Actual date Vs Planned Date of issuance of the Quantities BD as agreed during the Internal Kickoff Meeting and set in the Project charter | (Actual Date) - (Planned Date) To be Developed Under the Relevant Process (e.g. integration mgmt) |  | <=0
KPI-TM-03 | Process.TM.Dev-Sch. Process.TM.Exc&Ctrl-Schl. | Planning Engineer | Project Master Schedule (Works Programme) | Level of Accepted Risk | Critical Activities Ratio (Total Float = 0) % of Overall number of Activities | (Count of Critical Activities) ÷ (Count of all Programme Activities) |  | <= 8% to 10%
KPI-TM-04 | Process.TM.Dev-Sch. Process.TM.Exc&Ctrl-Schl. | Planning Engineer | Project Master Schedule (Works Programme) | Levelness of Resources | Near Critical Activities Ratio (Total Float < or = 10) % of Overall number of Activities | (Count of Activities with Total Float < or = 10) ÷ (Count of all Programme Activities) |  | <= 20%
KPI-TM-05 | Process.TM.Dev-Sch. | Planning Engineer | Project Master Schedule (Works Programme) | Level of Development of the Programme | Ratio of Concrete Construction Activities with Duration Greater than 30 Days | (Number of Activities with Duration > 30 Days) ÷ (Count of all Programme Activities) |  | <= 5%
KPI-TM-05A | Process.TM.Dev-Sch. | Planning Engineer | Project Master Schedule (Works Programme) | Level of Development of the Programme | Ratio of Finishing Construction Activities with Duration Greater than 30 Days | (Number of Activities with Duration > 30 Days) ÷ (Count of all Programme Activities) |  | < 15% to 25%
KPI-TM-06 | Process.TM.Dev-Sch. | Planning Engineer | Project Master Schedule (Works Programme) | Level of Development of the Programme | Total number of Activities | Count of all Programme Activities |  | betweeen 3,000 & 7,000 (Current project sizes)
KPI-TM-07 | Process.TM.Dev-Sch. | Planning Engineer | Project Master Schedule (Works Programme) | Schedule Logic | Number of Open Ended Activities | Count of Open Ended Activities |  | 0%
KPI-TM-08 | Process.TM.Dev-Sch. | Planning Engineer | Project Master Schedule (Works Programme) | Schedule Logic | Number of Activities without a Predecessor or Successor (Excluding Start & End) | Count of Activities without a Predecessor or Successor (Excluding Start & End) |  | 0%
KPI-TM-09 | Process.TM.Exc&Ctrl-Schl. | Project Manager | Timely Completion of Milestones | Time of Completion | Float - Interim completion for Internal & Contractual Milestones | Float (In Days) |  | >= 0
KPI-TM-09A | Process.TM.Exc&Ctrl-Schl. | Project Manager | Timely Completion of Milestones | Time of Completion | Float - Project completion for Internal & Contractual Milestones | Float (In Days) |  | >= 0
KPI-TM-10 | Process.TM.Exc&Ctrl-Schl. | Project Manager | Maintaining the Time Related High Risks to the Same level as per the Accepted levels at Project Initiation | Number of Critical Paths (Avoid Draining the Schedule Floats) | Ratio of actual number of critical paths Vs. baseline in Latest Update Vs in Base Line | (Count of Critical Paths in Latest Update) ÷ (Count of Critical Paths in Base Line Schedule) |  | < 1.1
KPI-TM-11 | Process.TM.Exc&Ctrl-Schl. | Project Manager | Timely Execution of Works | Earned Value of Executed Works | Schedule Perfomance Index - SPI Earned Value Vs Planned Value | EV ÷ PV |  | > =1
KPI-TM-12 | Process.TM.Exc&Ctrl-Schl. | Planning Engineer | Impacted Schedule | Correctness of Impacted Schedule | % Approval on Submitted Impacted Schedule | (Count of Impacted Schedule Submittals Approved) ÷ (Count of Impacted Schedule Submittals submitted) |  | >=90%
KPI-TM-13 | Process.TM.Exc&Ctrl-Schl. | CM Section Eng. Site Eng. | Timely Execution of Works | Number of Completed Activities | Planned Activities Completion Ratio Number of Completed Activities Vs Number of Planned Activities | (Cumulative Count of Completed Activities till this period) ÷ ((Cumulative Count of Planned Activities till this period) (PPC= Percent of Promises Completed could be used ) |  | >=1
KPI-TM-14 | Process.TM.LP. | Project Manager CM Section Eng. | Timely Detecting of Constraints During Planning Phase / ProjectManagement's Understaing of Project Needs | Correctness of Execution Constraints Action Plan | Constraints identification ratio Identified During Planning Vs Total Actual Constrains | (Count of Listed Constraints detected during the War Meeting of the Relevant Period) ÷ (Count of relevant Total Actual Constraints included in the Risk Register after completion of the planned Works for the same period) |  | >=1
KPI-TM-15 | Process.TM.LP. | CM Section Eng. Site Eng. Foreman | Timely Resolvement of Constraints During Planning Phase / Project Managemnets Ability to Resolve Problems | Ability of Project Management to Resolve Constraints in a Timely manner to avoid disruption of Works | Constraints resolution ratio Number of Resolved constraints Vs Actual Number of Constraints | (Count of resolved Constraints detected during the War Meeting of the Relevant Period) ÷ (Count of Listed Constraints detected during the War Meeting of the Relevant Period) |  | >=1
KPI-TM-16 | Process.TM.LP. | Section Eng. Site Eng. Foreman | Production | Production Rates | Production Rates Achievement ratio Actual Production Rates Vs Target Production Rates | (Actual Production Rates) ÷ (Target Production Rates) |  | >= 1
KPI-TM-17 | Process.TM.LP. | PMO | Project Control Tools | Efficiency & Accuracy | Efficiency & Accuracy of applied project control tools - Time Management | To be Developed Under the Management & Controls Process |  | >= 80%
KPI-TM-18 | Process.TM.Exc&Ctrl-Schl. | Project Manager | Project Master Schedule (Works Programme) | Customer Satisfaction | Customer Satisfaction - Time | To be Developed Under the Stakeholders Management Process |  | >= 80%

## KPIs Tracking-Dev-Sch Phase
KPIs Tracking Sheet - Time Management
Project: | ABC - Verdun
Phase: | Develop the Schedule Phase
Date: | 2015-12-21 | [8 empty] | Rev-A |  | Rev-B |  | Final Schedule
No. | Process Ref. | Owner | Key Result Area | Measurement Method of Results of KRA | Key Performance Indicator KPI | Calculation Method | Weight | Overall Target | Measure | [7 empty] | Weighted score | factor | Remarks Automatically generated based on KPIs scores | Reasons for Deviation
[10 empty] | Value | Status | Value | Status | Value | Status | Dev.*
KPI-TM-01 | Process.TM.Dev-Sch. Risk Mgmt. Process | Planning Engineer | Tender Planning Package | Captured Risk | Accuracy of Risk identification Risk captured at Tendering phase Vs Actual Risk after schedule development | (Count of identified risks at Tendering Phase) - (Count of identified Risks at Developing the schedule phase) To be Developed further Under the Risk Management Process | 0 | <=0 | Actual
[9 empty] | Target Upper limit | 0 |  | 0 |  | 0
KPI-TM-02 | Process.TM.Dev-Sch. Integration Management Process | Quantity Surveyor / Project level | Quantities Breakdown in accordance with the Agreed WBS | Date of issuance of the Quantities Breakdown Report | Timely completion of Quantities BD Actual date Vs Planned Date of issuance of the Quantities BD as agreed during the Internal Kickoff Meeting and set in the Project charter | (Actual Date) - (Planned Date) To be Developed Under the Relevant Process (e.g. integration mgmt.) | 0 | <=0 | Actual
[9 empty] | Target Upper limit | 0 |  | 0 |  | 0
KPI-TM-03 | Process.TM.Dev-Sch. Process.TM.Exc&Ctrl-Schl. | Planning Engineer | Project Master Schedule (Works Programme) | Level of Accepted Risk | Critical Activities Ratio (Total Float = 0) % of Overall number of Activities | (Count of Critical Activities) ÷ (Count of all Programme Activities) | 1 | <= 8% to 10% | Actual |  |  |  |  | 24% | 0 | 140% | 0 | 1 | There's a large number of Critical Activities
[9 empty] | Target Upper limit | 10% |  | 10% |  | 10%
KPI-TM-04 | Process.TM.Dev-Sch. Process.TM.Exc&Ctrl-Schl. | Planning Engineer | Project Master Schedule (Works Programme) | Levelness of Resources | Near Critical Activities Ratio (Total Float < or = 10) % of Overall number of Activities | (Count of Activities with Total Float < or = 10) ÷ (Count of all Programme Activities) | 1 | <= 20% | Actual |  |  |  |  | 13% | 1 | -35% | 1 | 1
[9 empty] | Target Upper limit | 20% |  | 20% |  | 20%
KPI-TM-05 | Process.TM.Dev-Sch. | Planning Engineer | Project Master Schedule (Works Programme) | Level of Development of the Programme | Ratio of Concrete Construction Activities with Duration Greater than 30 Days | (Number of Activities with Duration > 30 Days) ÷ (Count of all Programme Activities) | 1 | <= 5% | Actual |  |  |  |  | 18.24% | 0 | 264.8% | 0 | 1 | Concrete Construction Activities have long durations
[9 empty] | Target Upper limit | 5% |  | 5% |  | 5%
KPI-TM-05A | Process.TM.Dev-Sch. | Planning Engineer | Project Master Schedule (Works Programme) | Level of Development of the Programme | Ratio of Finishing Construction Activities with Duration Greater than 30 Days | (Number of Activities with Duration > 30 Days) ÷ (Count of all Programme Activities) | 1 | <15% to 25% | Actual
[9 empty] | Target Upper limit | 25% |  | 25% |  | 25%
KPI-TM-06 | Process.TM.Dev-Sch. | Planning Engineer | Project Master Schedule (Works Programme) | Level of Development of the Programme | Total number of Activities | Count of all Programme Activities | 1 | between 3,000 & 7,000 (Current project sizes) | Actual |  |  |  |  | 4422 | 1 |  | 1 | 1
[9 empty] | Target lower limit | 3000 |  | 3000 |  | 3000 |  | 1422
[9 empty] | Target Upper limit | 7000 |  | 7000 |  | 7000 |  | -2578
KPI-TM-07 | Process.TM.Dev-Sch. | Planning Engineer | Project Master Schedule (Works Programme) | Schedule Logic | Number of Open Ended Activities | Count of Open Ended Activities | 1 | 0 | Actual
[9 empty] | Target Upper limit | 0 |  | 0 |  | 0
KPI-TM-08 | Process.TM.Dev-Sch. | Planning Engineer | Project Master Schedule (Works Programme) | Schedule Logic | Number of Activities without a Predecessor or Successor (Excluding Start & End) | Count of Activities without a Predecessor or Successor (Excluding Start & End) | 1 | 0 | Actual
[9 empty] | Target Upper limit | 0 |  | 0 |  | 0
Overall KPIs Score | [13 empty] | 50% | 50% |  | 2 | 4
General Remarks
* Deviation from Target
100%
0%

## KPIs Tracking-Exec-M&C Phase
KPIs Tracking Sheet - Time Management | [24 empty] | KPIs Historical Data - Time Management
Project: | ABC - Verdun
Phase | Execution and Monitoring & Controlling Phase | [8 empty] | Previous Month |  |  |  | Latest Month |  |  |  |  | Comparison
Date: | 2015-12-21
No. | Process Ref. | Owner | Key Result Area | Measurement Method of Results of KRA | Key Performance Indicator KPI | Calculation Method | Weight | Overall Target | Measure | 2015-10-01 |  |  |  | 2015-11-01 | [6 empty] | Remarks Automatically generated based on KPIs scores | Reasons for Deviation &/or decrease in trend | Actions required for next month |  | Measure | Monitoring & Controlling Phase
[10 empty] | Value | Status | Weighted Score | Factor | Value | Status | Dev. from target | Weighted Score | Factor | Trend | Dev. From prev. week |  |  |  | 1 | time axis 2015-01-01 to 2018-12-01
KPI-TM-03 | Process.TM.Dev-Sch. Process.TM.Exc&Ctrl-Schl. | Planning Engineer PM | Project Master Schedule (Works Programme) | Level of Risk | Critical Activities Ratio (Total Float = 0) % of Overall number of Activities | (Count of Critical Activities) ÷ (Count of all Programme Activities) | 1 | < 8% to 10% | Actual | 20.08% | 0 | 0 | 1 | 27.27% | 0 | 172.7% | 0 | 1 | 0 | 35.81% | Large Number of Critical Activities |  |  | 2 | Actual | 2015-10-01: 20.08%; 2015-11-01: 27.27%
[9 empty] | Plan | [14 empty] | 3 | Plan
[9 empty] | Target upper limit | 10% |  |  |  | 10% | [6 empty] | The Number of Critical Activities has increased |  |  | 4 | Target | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
KPI-TM-04 | Process.TM.Dev-Sch. Process.TM.Exc&Ctrl-Schl. | Planning Engineer PM | Project Master Schedule (Works Programme) | Levelness of Resources | Near Critical Activities ratio (Total Float < or = 10) % of Overall number of Activities | (Count of Activities with Total Float < or = 10) ÷ (Count of all Programme Activities) | 1 | < 20% | Actual | 19.4% | 1 | 1 | 1 | 14.3% | 1 | -28.5% | 1 | 1 | 2 | -26.29% |  |  |  | 5 | Actual | 2015-10-01: 19.4%; 2015-11-01: 14.3%
[9 empty] | Plan | [14 empty] | 6 | Plan
[9 empty] | Target upper limit | 20% |  |  |  | 20% | [9 empty] | 7 | Target | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20%
KPI-TM-09 | Process.TM.Exc&Ctrl-Schl. | Project Manager | Timely Completion of Milestones | Time of Completion | Float - Interim completion for Internal & Contractual Milestones | Float (In Days) | 1 | >= 0 | Actual | 18 | 1 | 1 | 1 | -2 | 0 | -2 | 0 | 1 | 0 | -111.1% | Large Number of Near Critical Activities |  |  | 8 | Actual | 2015-10-01: 18; 2015-11-01: -2
[9 empty] | Plan | [14 empty] | 9 | Plan
[9 empty] | Target lower limit | 0 |  |  |  | 0 | [6 empty] | The Number of Near Critical Activities has increased |  |  | 10 | Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KPI-TM-09A | Process.TM.Exc&Ctrl-Schl. | Project Manager | Timely Completion of Milestones | Time of Completion | Float - Project completion for Internal & Contractual Milestones | Float (In Days) | 1 | >= 0 | Actual | -12 | 0 | 0 | 1 | -26 | 0 | -26 | 0 | 1 | 0 | -14 | The Project is in Delay |  |  | 11 | Actual | 2015-10-01: -12; 2015-11-01: -26
[9 empty] | Plan | [14 empty] | 12 | Plan
[9 empty] | Target lower limit | 0 |  |  |  | 0 | [6 empty] | The Overall Project Estimated duration has Increased |  |  | 13 | Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KPI-TM-10 | Process.TM.Exc&Ctrl-Schl. | Project Manager | Maintaining the Time Related High Risks to the Same level as per the Accepted levels at Project Initiation | Number of Critical Paths (Avoid Draining the Schedule Floats) | Ratio of actual number of critical paths Vs. baseline in Latest Update Vs in Base Line | (Count of Critical Paths in Latest Update) ÷ (Count of Critical Paths in Base Line Schedule) | 1 | < 1.1 | Actual | 0.91667 | 1 | 1 | 1 | 0.75 | 1 | -31.82% | 1 | 1 | 2 | -18.18% |  |  |  | 14 | Actual | 2015-10-01: 0.91667; 2015-11-01: 0.75
[9 empty] | Plan | [14 empty] | 15 | Plan
[9 empty] | Target upper limit | 1.1 |  |  |  | 1.1 | [9 empty] | 16 | Target | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
KPI-TM-11 | Process.TM.Exc&Ctrl-Schl. | Project Manager | Timely Execution of Works | Earned Value of Executed Works | Schedule Performance Index - SPI Earned Value Vs Planned Value | EV ÷ PV | 1 | > =1 | Actual | 1.38 | 1 | 1 | 1 | 1.15 | 1 | 15% | 1 | 1 | 0 | -16.67% |  |  |  | 17 | Actual | 2015-10-01: 1.38; 2015-11-01: 1.15
[9 empty] | Plan | [14 empty] | 18 | Plan
[9 empty] | Target lower limit | 1 |  |  |  | 1 | [6 empty] | There's a slippage from the schedule |  |  | 19 | Target | bar: 2015-01-01 to 2018-12-01
KPI-TM-12 | Process.TM.Exc&Ctrl-Schl. | Planning Engineer | Impacted Schedule | Correctness of Impacted Schedule | % Approval on Submitted Impacted Schedule | (Count of Impacted Schedule Submittals Approved) ÷ (Count of Impacted Schedule Submittals submitted) | 1 | >=90% | Actual | [14 empty] | 20 | Actual
[9 empty] | Plan | [11 empty] | The Approval of all submitted impacted schedules hasn’t been achieved |  |  | 21 | Plan
[9 empty] | Target lower limit | 90% |  |  |  | 90% | [9 empty] | 22 | Target | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
KPI-TM-13 | Process.TM.Exc&Ctrl-Schl. | CM Section Eng. Site Eng. | Timely Execution of Works | Number of Completed Activities | Planned Activities Completion Ratio Number of Completed Activities Vs Number of Planned Activities | (Count of Completed activities) ÷ (Count of Planned Activities) (Refer to the Last Planner System) | 1 | >=1 | Actual | 0.92251 | 0 | 0 | 1 | 0.90196 | 0 | -9.804% | 0 | 1 | 0 | -2.227% | The progress is less than planned |  |  | 23 | Actual | 2015-10-01: 0.92251; 2015-11-01: 0.90196
[9 empty] | Plan | [14 empty] | 24 | Plan
[9 empty] | Target lower limit | 1 |  |  |  | 1 | [6 empty] | There's a slippage from the schedule |  |  | 25 | Target | bar: 2015-01-01 to 2018-12-01
KPI-TM-14 | Process.TM.LP. | Project Manager CM Section Eng. | Timely Detecting of Constraints During Planning Phase / Project Management's Understating of Project Needs | Correctness of Execution Constraints Action Plan | Constraints identification ratio Identified During Planning Vs Total Actual Constrains | (Count of Listed Constraints detected during the War Meeting of the Relevant Period) ÷ (Count of relevant Total Actual Constraints included in the Risk Register after completion of the planned Works for the same period) | 1 | >=1 | Actual | [14 empty] | 26 | Actual
[9 empty] | Plan | [14 empty] | 27 | Plan
[9 empty] | Target lower limit | 1 |  |  |  | 1 | [9 empty] | 28 | Target | bar: 2015-01-01 to 2018-12-01
KPI-TM-15 | Process.TM.LP. | CM Section Eng. Site Eng. Foreman | Timely Resolution of Constraints During Planning Phase / Project Management's Ability to Resolve Problems | Ability of Project Management to Resolve Constraints in a Timely manner to avoid disruption of Works | Constraints resolution ratio Number of Resolved constraints Vs Actual Number of Constraints | (Count of resolved Constraints detected during the War Meeting of the Relevant Period) ÷ (Count of Listed Constraints detected during the War Meeting of the Relevant Period) | 1 | >=1 | Actual | [14 empty] | 29 | Actual
[9 empty] | Plan | [14 empty] | 30 | Plan
[9 empty] | Target lower limit | 1 |  |  |  | 1 | [9 empty] | 31 | Target | bar: 2015-01-01 to 2018-12-01
KPI-TM-16 | Process.TM.LP. | Section Eng. Site Eng. Foreman | Production | Production Rates | Production Rates Achievement Actual Production Rates Vs Target Production Rates | (Actual Production Rates) ÷ (Target Production Rates) | 1 | >=1 | Actual | [14 empty] | 32 | Actual
[9 empty] | Plan | [14 empty] | 33 | Plan
[9 empty] | Target lower limit | 1 |  |  |  | 1 | [9 empty] | 34 | Target | bar: 2015-01-01 to 2018-12-01
KPI-TM-17 | Process.TM.LP. | PMO | Project Control Tools | Efficiency & Accuracy | Efficiency & Accuracy of applied project control tools | To be Developed Under the Management & Controls Process | 1 | 80% | Actual | [14 empty] | 35 | Actual
[9 empty] | Plan | [14 empty] | 36 | Plan
[9 empty] | Target lower limit | 80% |  |  |  | 80% | [9 empty] | 37 | Target | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80%
KPI-TM-18 | Process.TM.Exc&Ctrl-Schl. | Project Manager | Project Master Schedule (Works Programme) | Customer Satisfaction | Customer Satisfaction ratio - Time | To be Developed Under the Stakeholders Management Process |  | >= 80% | Actual | [14 empty] | 35 | Actual
| Process.TM.Exc&Ctrl-Schl. | Project Manager | Project Master Schedule (Works Programme) | Customer Satisfaction | Customer Satisfaction - Time | To be Developed Under the Stakeholders Management Process |  | >= 80% | Plan | [14 empty] | 36 | Plan
[9 empty] | Target lower limit | 80% |  |  |  | 80% | [9 empty] | 37 | Target | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 80%
38
Overall KPIs Score | [9 empty] | 57.14% | 57.14% | 4 | 7 | 42.86% | 42.86% |  | 3 | 7 | 0 | -25% | The Overall KPIs score has declined |  |  | 39 | Actual | 2015-10-01: 57%; 2015-11-01: 43%
40
Key Trend lines
100%
0%
General Remarks

## KPIs Dashboard-Project
KPIs Dashboard & Monthly Summary - Time Management
Project: | ABC - Verdun
Phase: | Execution and Monitoring & Controlling
Date: | 2015-12-10
Trendlines
Summary
Summary of KPIs |  | Descriptive summary & Action Plan
Last Month Completed Works & Successes:
Next Month Plan:
Last month Critical Notes, deviations & learnings :
Next Month Corrective & preventive Action List:
Snapshot of the KPIs tracking sheet

## KPIs Dashboard-Area-Comb-Sample
KPIs Dashboard & Monthly Summary - Time Management
Dpt-Area: |  | Planning-Lebanon
Month: |  | 2015-12-10
Status Per Project
| ABC Project |  | Project 2 |  | Project 3
Notes
Summary
Results of all projects combined
Summary of All KPIs |  |  |  | Descriptive summary & Action Plan
Last Month Completed Works & Successes:
Next Month Plan:
Last month Critical Notes, deviations & learnings :
Next Month Corrective & preventive Action List:

## KPIs Dashboard-Area-Comb-Sa (2
KPIs Dashboard & Monthly Summary - Time Management
Dpt-Area: |  | Planning-Lebanon
Month: |  | 2015-12-10
Status Per Project
| ABC Project |  | Project 2 |  | Project 3
Notes
Summary
Results of all projects combined
Summary of All KPIs |  |  |  | Descriptive summary & Action Plan
Last Month Completed Works & Successes:
Next Month Plan:
Last month Critical Notes, deviations & learnings :
Next Month Corrective & preventive Action List: