## Sheet1
Process Name | Improvement Area | Description of Issue | Type | Notes
Field Services + Support | Budget for Estimating | Not knowing that Estimating need a budget. Not asking the right question about the need of the project. Not communicating on the size and man power for the project. | Communication & Input
Field Services + Support | VOIP - Obtain Phones | Not knowing when the project true start date is. Waiting until the trailer is on site to not have to pay for something if it isn't on site. | Coordination
Field Services + Support | VOIP - Provision phone #s |  | Coordination & Process Standards
Field Services + Support | Site survey |  | Logistics
Field Services + Support | Communicate w/Ops |  | Communication & Validation
Field Services + Support | MIFI |  | Process standards variation
Field Services + Support | Trailer On-Site |  | Coordination & Commitment
Field Services + Support | Asset Tags |  | Process Standards
Field Services + Support | Power Setup |  | Coordination & Commitment
Field Services + Support | Site Setup Equipment |  | Coordination & Process Standards
Field Services + Support | Test VPN |  | Process Standards
Field Services + Support | Call site for checkup |  | Communication & Input
Field Services + Support | Jobsite monthly visits |  | Coordination & Commitment
Field Services + Support | Weekly Status Report |  | Process Standards
Field Services + Support | Jobsite Breakdown |  | Coordination & Process Standards
Field Services + Support | Trailer Removal - Ops |  | Communication & Coordination & Process Standards
Field Services + Support | Cancel Internet |  | Coordination & Communication
Field Services + Support | Copier Pickup |  | Coordination & Communication
Field Services + Support | Refurbish Equipment + QC |  | Process Standards
Field Services + Support | Inventory Management |  | Process standards variation
Field Services + Support | Restock Equipment |  | Process standards variation
Field Services + Support | VOIP - Remove phones |  | Communication & Process Standards
Root causes |  |  | Process standards, Communication