## Process Walk Planning Timeline
Process Walk Planning Timeline
Time Frame | Description | Task Owner | Date Done
8 weeks prior | Identify the core process to be "walked"
8 weeks prior | Assign responsibilities for planning the process walk and handling the details
6-8 weeks prior | Schedule Preliminary Process Walk Discussion with Process Owners
6 weeks prior | Conduct Preliminary Process Walk Discussion with Process Owners
6 weeks prior | Schedule Process Walk Planning Meeting
4-5 weeks prior | Conduct the Process Walk Planning Meeting
4 weeks prior | Schedule Process Walk Date
4 weeks prior | Reserve Facilities and Address Location
4 weeks prior | Send stakeholders an invitation to the stakeholder presentation
(typically scheduled on the last day of Process Walk)
4 weeks prior | Send introduction letter/e-mail to participants
3 weeks prior | Send e-mail invite to kick-off to interviewees for the Process Walk (those that will not participate in the entire event
2-3 weeks prior | Send e-mail invites to the Interviewees that includes a window of time that their interview will occur during the Process Walk
2-3 weeks prior | Reserve needed equipment:
Laptop, Projector, Projector screen, Flipchart easels and paper
2-3 weeks prior | Arrange for room set-up, provide a room layout to facilities
2-3 weeks prior | Arrange for meals, snacks, coffee, etc.
2 weeks prior | If data has been gathered on the process, review, graph, and incorporate into the Process Walk Slide Presentation
2 weeks prior | Review the Supplies Checklist and confirm who is bringing what
2 weeks to 2 days prior | If there will be more than one facilitator, discuss facilitator split (Primary, secondary facilitation roles)
2 weeks prior | Prepare supplemental materials, event evaluations, output templates and ice-breaker activities
2 weeks prior | If necessary, ship/print materials as needed
3-5 days prior | If shipping materials, confirm arrival of materials prior to event
3-5 days prior | Send reminder, and/or the detailed agenda to participants
Confirm participation of participants
3-5 days prior | Discuss kick-off and closing session responsibilities with Primary Process Owner
3-5 days prior | Ask interviewees to plan to share process work during the interview. Sometimes the process isn't running or work isn't available, so planning to share work that has been done is a second option
3-5 days prior | Confirm refreshment arrangements
1-3 days prior | Identify key site contact for DAY OF ARRIVAL (name, phone, e-mail) to gain site/room access
1-3 days prior | Confirm date/day/time of arrival on site with key contact
1-3 days prior | Confirm room set-up and equipment instructions
1-3 days prior | Send out a pre-event communication to those that may see or be affected by the Process Walk Event Ð keep people informed, share excitement
DAY OF | Arrive early to check room setup, equipment use, and arrange materials