## As Is_Management System_Draft
Project Management System - As Is State
Period | Forecast (Initiation) | Plan | Control |  | Report
Project
Quarterly
Monthly
Fortnightly
Weekly
Daily
| Prepared by Head Office |  |  | Consistently applied |  | Occasionally applied
P&L Report
DRAFT
Target Budget (Forecasted Cost)
Monthly Progress report
Detailed Project Schedule
Schedule Progress updates - Planner & Site Engineers
Action Items
Daily Timesheet (SIC)
Timecards
Balance Cost
Milestones high level tender schedule, could include detailed concrete 3-months look-ahead)
Project Organization Structure
Cost Ctrl Report
Weekly Progress Report
Same month
Daily Report - Direct Manpower
Daily report - All manpower, list of activities, Equipment, SUB. List...
Forecasted Profit
2 weeks look ahead for specific activities i.e. tiling
Progress meetings with Subcontractors
Action Items
Planning
Cost Control
Progress Meeting with client, engineer
Subcontractor Appraisal
Forecasted Cash Flow
Logistics / Arrangement /Safety Plans
Material Schedule
Shop dwgs Schedule
Equipment Schedule
Employee Assessment (yearly or before departure)
Logs (master log, shop dwg, material, delivery, vov, npv, claim, accounting...)
MoM & Action Log
Project Data Backup
Main Payment (owner's payment)
Sub/Sup/Labor Payment statements
Packaging Strategy & Targets
Detailed Procurement Monitoring Sheet
Procurement
Monthly Procurement report
HO
HO
HO
HO
HO
HO
HO
Management Review Meeting
Staff Plan
Budget Per Item
HO
HO
HO
HO
Site Staff Needs & Updated Org. Chart
Onsite Inventory List -
For reconciliation
HO
POC (Percentage Of Completion - Cost)
HO
Manpower overview
HO
Cost Monitoring Meeting PM, CM, Cost Ctrl Team
Programme Updates