## Rapid Imp. Planning Timeline
Rapid Improvement Event Planning Timeline
Time Frame | Description | Task Owner | Date Done
4-6 weeks prior | Schedule Preliminary Rapid Improvement Event Discussion with Process Owners
4-6 weeks prior | Conduct Preliminary Rapid Improvement Event with Process Owners
6 weeks prior | Schedule Rapid Improvement Planning Meeting
4-6 weeks prior | Conduct the Rapid Improvement Planning Meeting
4 weeks prior | Schedule Rapid Improvement Date
4 weeks prior | Finalize agenda for the Rapid Improvement Event
4 weeks prior | Reserve Facilities and Address Location
4 weeks prior | Determine stakeholders for event and send an invitation to the stakeholder presentation
(typically scheduled on the last day of Rapid Improvement Event
4 weeks prior | Send communication e-mail to participants re: event
2-3 weeks prior | Reserve needed equipment:
Laptop, Projector, Projector screen, Flipchart easels and paper
If a 5S event, gather appopriate supplies and materials; identify SORT area
2-3 weeks prior | Arrange for room set-up, provide a room layout to facilities
2-3 weeks prior | Arrange for meals, snacks, coffee, etc.
2 weeks prior | Finish up remaining pre-work for the Rapid Improvement Event
2 weeks prior | Review the Supplies Checklist and confirm who is bringing what
2 weeks to 2 days prior | If there will be more than one facilitator, discuss facilitator split (Primary, secondary facilitation roles)
2 weeks prior | Prepare supplemental materials, event evaluations, output templates and ice-breaker activities
2 weeks prior | If necessary, ship/print materials as needed
3-5 days prior | If shipping materials, confirm arrival of materials prior to event
3-5 days prior | Send reminder, and/or the detailed agenda to participants
Confirm participation of participants
3-5 days prior | Discuss kick-off and closing session responsibilities with Primary Process Owner
3-5 days prior | Confirm refreshment arrangements
1-3 days prior | Identify key site contact for DAY OF ARRIVAL (name, phone, e-mail) to gain site/room access
1-3 days prior | Confirm date/day/time of arrival on site with key contact
1-3 days prior | Confirm room set-up and equipment instructions
DAY OF | Arrive early to check room setup, equipment use, and arrange materials