## Cost Control
SIPOC Diagram
Department / Project: |  |  |  | Process Name: |  |  |  | Process Owner:
Operations |  |  |  | Cost control checking, compilation and reporting |  |  |  | Operations Department
Supplier | ► | Input | ► | Process | ► | Output | ► | Customer
Site Cost Control Engineer |  | Monthly Concrete Cost Control Report |  | Review Breakdown of the dry Budget (SMELO) |  | Adjustments and Comments |  | Site Cost Control Engineer
|  | -Labor Forecast Total Profit / Loss and actual cost per unit versus Budget |  | Double check and Adjust the cost codes |  | Reasons and corrective actions by meetings, phone calls or emails |  | Area General Manager, Project Manager, Construction Manager and Site Cost Control Engineer
|  | -Material Forecast Total Profit / Loss and actual cost per unit versus budget |  | Check the quantity with respect to progress |  | Monthly Concrete Cost Control Report |  | Corporate Department (monthly) and Estimation Department (every three to four months)
|  | -Subcontractor Forecast Total Profit / Loss and actual cost per unit versus budget |  | Double check the subletting rates |  | Global Monthly Cost Report |  | Top management, Area General Manager, Contracts Manager, Corporate Manager, Estimation Manager
|  | -Equipment and other Forecast Total Profit / Loss and actual cost per unit |  | Analyzing Productivity, waste and $/MHR monitoring
|  | -Revised total estimated quantity versus revised BOQ quantity |  | Profit Loss checking and variance with previous month
Prepare the Global Monthly Cost Report
Site Cost Control Engineer |  | Monthly project cost control Report |  | Review Breakdown of the selling, dry Budget and the subletting |  | Adjustments and Comments |  | Site Cost Control Engineer
|  | -Indirect, concrete and subletting |  | Double check and Adjust the cost codes |  | Reasons and corrective actions by meetings, phone calls or emails |  | Area General Manager, Project Manager, Construction Manager and Site Cost Control Engineer
|  |  |  | Forecast and actual profit/Loss checking by code and variance with previous month |  | Monthly project cost control Report |  | Corporate Department (monthly)
|  |  |  | Checking the receivables versus the total budget and the payables versus the forecast total cost |  | Global Monthly Cost Report |  | Top management, Area General Manager, Contracts Manager, Corporate Manager, Estimation Manager
Prepare the Global Monthly Cost Report
Input |  |  |  | Tools & Techniques |  | Output
Requirements |  | Measurements / Metrics |  |  |  | Requirements |  | Measurements / Metrics
Templates/Reports used
Other Notes: